## Plan of Action
Plan of Action — Todozee Past-Life (Gatha Janma) Insight API
Local Gemma 4 + FastAPI on AWS GPU (Mumbai) • Status: PLANNED — execution starts once the gated-model HF token is provided
# | Phase | Action item | Status | Owner | Priority | Notes
1 | 0. Planning & prerequisites | Clone repo and analyze the Past-Life FastAPI app | Done | Kishore | - | Local Gemma 4 + astrology; Past_Life.py on port 7002
2 |  | Confirm GPU requirement; choose instance type & region | Done | User + Kishore | - | g5.xlarge (A10G 24GB), ap-south-1 (Mumbai)
3 |  | Verify tooling (AWS CLI, Terraform, credentials) | Done | Kishore | - | Account 637560253183, TF 1.15
4 |  | Obtain HF token + accept gemma-4 gated license | Pending | User | High | BLOCKER: model is gated; also confirm model id is published
5 |  | Put HF token into SSM Parameter Store (SecureString) | To do | User | High | /todozee-past-life/hf_token ; kept out of TF state
6 | 1. Infrastructure (Terraform) | Write IaC: EC2 g5, EIP, SG, IAM, SSM read, CloudWatch | To do | Kishore | - | main.tf, variables, outputs, user_data
7 |  | Resolve G-instance vCPU quota (request increase if needed) | To do | User + Kishore | High | Mumbai G-quota was tight on prior GPU deploy
8 |  | terraform apply - provision instance + EIP | To do | Kishore | - | Only after HF token in SSM
9 | 2. Application bootstrap | Install Python 3.13 (deadsnakes) + cu128 torch + deps | To do | user_data | - | App requires py>=3.13; DLAMI ships 3.10
10 |  | Download gated Gemma 4 (~10GB) to EBS-backed HF cache | To do | user_data | - | Uses HF_TOKEN from SSM
11 |  | systemd service (Past_Life.py :7002, model preload) | To do | user_data | - | todozee-past-life.service
12 |  | Verify GPU inference (~5s/insight, not CPU fallback) | To do | Kishore | - | Confirm CUDA path + A10G VRAM use
13 | 3. Networking & HTTPS | Add DNS A-record (Cloudflare) | To do | User | - | pastlife.chatbucket.chat -> EIP
14 |  | Caddy auto-HTTPS / Lets Encrypt cert | To do | Kishore | - | Reverse proxy 127.0.0.1:7002; auto-renew
15 | 4. Monitoring & alerting | CloudWatch alarms + agent (mem/disk/GPU) | To do | Kishore | - | status-check, CPU>90%; namespace TodozeePastLife
16 |  | Route 53 health check + SNS email | To do | User + Kishore | - | HTTPS /health probe; confirm email sub
17 | 5. CI/CD | Push terraform + workflows to GitHub | To do | User + Kishore | - | Secrets: EC2_HOST, EC2_SSH_KEY
18 |  | Deploy workflow (SSH git-pull + restart + health) | To do | Kishore | - | CI gate -> deploy -> health -> rollback
19 | 6. Hardening (industry standard) | Remote S3 state + S3-native locking | To do | Kishore | - | Versioned/encrypted bucket
20 |  | Pinned app dependency lockfile + provider lock | To do | Kishore | - | requirements.lock.txt + .terraform.lock.hcl
21 |  | Keyless OIDC roles (plan + apply) | To do | Kishore | - | No long-lived AWS keys in CI
22 |  | terraform plan-on-PR + manual gated apply | To do | Kishore | - | Reuse shared OIDC provider
23 |  | Auto + manual rollback (live-tested) | To do | Kishore | - | Records last-good SHA
24 | 7. Documentation | DEPLOYMENT.md runbook | To do | Kishore | - | Architecture, ops, teardown
25 |  | AWS services inventory (xlsx) | Done | Kishore | - | aws-services.xlsx
26 |  | Estimation + Plan of Action (these files) | Done | Kishore | - | ESTIMATION_PLAN + PLAN_OF_ACTION
27 | 8. Remaining / recommended | Configure 'production' environment required-reviewer | Pending | User | Medium | GitHub UI; needs repo admin
28 |  | Lock SSH (port 22) SG to a specific IP | Recommended | User | Medium | Default 0.0.0.0/0
29 |  | Add ruff + pip-audit CI gate | Optional | Kishore | Low | Deferred - deployment-only, no app changes
30 |  | Evaluate HA/multi-AZ (containerize -> ECS) | Future | User | Low | Tier 3; cost+quota dependent

## Timeline
Deployment Timeline — Todozee Past-Life Insight API
Day 0 = Tue Jun 30, 2026 • Core phases 1–7 projected across ~9 business days • Begins when the HF token is provided
Milestone | Phase | Target window | Date | Status
HF token obtained + license accepted (prereq) | 0 | Day 0 | 2026-06-30 | Pending
Infra provisioned (EC2 GPU + EIP) | 1 | Day 2 | 2026-07-02 | Planned
App live on GPU (insight verified) | 2 | Day 4 | 2026-07-03 | Planned
Public HTTPS live (DNS + cert) | 3 | Day 4 | 2026-07-03 | Planned
Monitoring + email alerts active | 4 | Day 5 | 2026-07-06 | Planned
CI/CD pipeline green end-to-end | 5 | Day 6 | 2026-07-07 | Planned
Hardening done (state/deps/OIDC/rollback) | 6 | Day 7-9 | 2026-07-10 | Planned
Documentation delivered | 7 | Day 9 | 2026-07-10 | Planned
Lock SSH SG to specific IP | 8 | Week 2 | by 2026-07-17 | Recommended
Configure production reviewer gate | 8 | Week 2 | by 2026-07-17 | Pending
Optional: ruff + pip-audit gate | 8 | Backlog | - | Optional
Future: HA / multi-AZ (ECS) | 8 | Backlog | - | Future