## Estimation Plan
Estimation Plan — Todozee Past-Life (Gatha Janma) Insight API
Local Gemma 4 + FastAPI on AWS GPU • Start: Tue Jun 30, 2026 • Core effort: 9.25 person-days • Est. finish: Fri Jul 10, 2026 • Status: PLANNED
# | Phase | Task | Effort (days) | Planned start | Planned end | Owner | Dependency
1 | 0. Planning | Requirements analysis, repo review & instance/region sizing | 0.5 | Jun 30 (Tue) | Jun 30 (Tue) | Kishore | -
2 |  | Obtain HF token + accept gemma-4 gated license [BLOCKER] | 0.25 | Jun 30 (Tue) | Jun 30 (Tue) | User | Planning
3 | 1. Infrastructure | Write Terraform IaC (EC2 g5, EIP, SG, IAM, SSM, CW) | 1 | Jul 01 (Wed) | Jul 01 (Wed) | Kishore | Planning
4 |  | Resolve G-instance GPU quota & provision (apply) | 0.5 | Jul 02 (Thu) | Jul 02 (Thu) | Kishore | IaC + HF token
5 | 2. App bootstrap | Python 3.13 + cu128 torch + deps + gated model download + systemd | 1 | Jul 02 (Thu) | Jul 03 (Fri) | Kishore | Provision
6 |  | Verify GPU inference (insight ~5s, not CPU fallback) | 0.5 | Jul 03 (Fri) | Jul 03 (Fri) | Kishore | Bootstrap
7 | 3. Networking/HTTPS | DNS A-record + Caddy auto-HTTPS (cert) | 0.5 | Jul 03 (Fri) | Jul 03 (Fri) | Kishore | Provision
8 | 4. Monitoring | CloudWatch alarms/agent (mem/disk/GPU) + Route53 health + SNS | 1 | Jul 06 (Mon) | Jul 06 (Mon) | Kishore | Provision
9 | 5. CI/CD | GitHub workflows + secrets + green verify | 1 | Jul 07 (Tue) | Jul 07 (Tue) | Kishore | App live
10 | 6. Hardening | Remote S3 state + S3-native locking | 0.5 | Jul 08 (Wed) | Jul 08 (Wed) | Kishore | CI/CD
11 |  | Pinned app deps + provider lock | 0.5 | Jul 08 (Wed) | Jul 08 (Wed) | Kishore | CI/CD
12 |  | Keyless OIDC roles (plan + apply) | 0.5 | Jul 09 (Thu) | Jul 09 (Thu) | Kishore | CI/CD
13 |  | terraform plan-on-PR + gated apply in CI | 0.5 | Jul 09 (Thu) | Jul 09 (Thu) | Kishore | OIDC
14 |  | Auto + manual rollback (with live test) | 0.5 | Jul 10 (Fri) | Jul 10 (Fri) | Kishore | CI/CD
15 | 7. Documentation | Runbook + AWS inventory + plan docs | 0.5 | Jul 10 (Fri) | Jul 10 (Fri) | Kishore | All
16 | 8. Follow-up | Lock SSH SG to a specific IP | 0.25 | Week 2 | by Jul 17 | User | post-core
17 |  | Configure production reviewer gate | 0.25 | Week 2 | by Jul 17 | User | post-core
18 |  | ruff + pip-audit CI gate (optional) | 0.5 | Backlog | Backlog | Kishore | post-core
19 |  | Evaluate HA / multi-AZ (ECS) | 2 | Backlog | Backlog/Future | User | post-core
|  | TOTAL CORE EFFORT (phases 0–7) | 9.25
Calendar Gantt — core work (business days)
Task | Jun 30 Tue | Jul 01 Wed | Jul 02 Thu | Jul 03 Fri | Jul 06 Mon | Jul 07 Tue | Jul 08 Wed | Jul 09 Thu | Jul 10 Fri
Requirements, repo review & sizing
Obtain HF token + accept gemma-4 license
Write Terraform IaC (g5, EIP, SG, IAM, SSM, CW)
Resolve GPU quota & provision (apply)
Py3.13 + cu128 torch + deps + model + systemd
Verify GPU inference (~5s/insight)
DNS A-record + Caddy auto-HTTPS
CloudWatch + Route53 health + SNS
GitHub CI/CD workflows + secrets
Remote S3 state + locking
Pinned deps + provider lock
Keyless OIDC roles
plan-on-PR + gated apply
Auto + manual rollback (live test)
Runbook + inventory + plan docs
Milestones | Kickoff |  | App live | HTTPS+Mon | CI/CD |  |  | Hardened